Timeline for planning and implementing your CPR Training Events

1-2 months before event

- Designate a primary leader for your event. Allocate other roles to other members of the group. Meet to assign other duties on this timeline for planning/implementation.

- Contact administration and the head of Residence Life about event (the order of this communication may change depending on your school). Register event and discuss funding options.

- Plan out scope of event (estimate number of participants, number of trainings over what time period) and budget required for event.

1 month before event

- Order CPR in Schools Training Kit(s)™ from American Heart Association (Click Buy Now at heart.org/cprinschools)

- Reserve location on campus to hold training if needed. Fill out appropriate paperwork for school related to reserving the building and a TV/Projection System/DVD player.

- Schedule email blast to students if possible.

3 weeks before event

- Print flyers and posters.

- If school requires approval of promotional materials, get approval prior to printing.

2-3 weeks before event (or as appropriate for your school)

- Put up flyers and posters in areas around campus or residence hall.

- Order food (timing of ordering depends on university).

- Send out first email blast to residence hall floor.

- Contact other RAs and have them promote event in their residence halls.

- Create Facebook/social media event.

1-2 weeks before event

- Send out two email reminders to students to encourage registration.

- Update Facebook event, post reminders on all social media sites, increase excitement.

- Post videos from the AHA CPR in Schools website about CPR (See www.heart.org/cprinschools)

1 week before event

- Order food for event (timing of ordering depends on University).

- Have the students leading the training familiarize themselves with the CPR in Schools Training Kit™ (watch DVD and review lesson plan) and watch the webinar available once kits are purchased.

Day before the event

- Send email reminder to students who have registered.

Day of event

- Bring CPR training kit, giveaways, and incentives to location.

- Pick up food.

- Set up manikins and handouts before event starts.

- Test TV/Projection System/DVD player.

- Facilitate training.